## Slide 1
TS: Nguyễn Xuân Quang
MODULE 10:
ESCO PROJECT DEVELOPMENT PROCESS

## Slide 2: Project development process
  ESCOs use methods to sell their energy services to customers
  The sales process has been applied to allow high-level concept sales to customers in an effective way
  Most enterprise owners have no experience before starting with ESCOs and EPCs
  This is a step-by-step process like building a relationship
Notes: Going on a journey to achieve energy efficiency
ESCO is the guide!
ESCOs know the road – make it easy

## Slide 3: Project dEVELOPMENT process
The project development process can be broken down into a more detailed series of events/elements in preparation for the signing of an energy performance contract (EPC).
The process for all ESCOs is not the same, the details of the process are part of the business model and make each ESCO unique.
Here we present best practices from years of experience.
Notes: Next: Process
It’s not a one size fit all process. It could be quite different from ESCO to ESCO. This is what will make your esco different from others.

## Slide 4: Project development process
Survey/ Opportunity Assessment
First call or first meeting
Confirm creditworthiness (level 1)
Customer capacity
Present concepts to clients
Send survey questions to customers
Notes: All these points are presented in the next slides

## Slide 5: Project development process
Customer signs letter of interest (LOI)
Preliminary energy audit
Confirm creditworthiness (level 2)
Present preliminary energy audit results to client
Investment level audit phase agreement or general framework contract
Customer signs agreement.
Investment grade audit (IGA)

## Slide 6: Project development process
Client discusses/accepts investment grade audit results
Final risk assessment
Financial planning and funding sources
Complete contract
The customer signs the performance contract or appendices of the framework contract.
Notes: Final risk assessment: risk assessment should be a constant preoccupation from the WTA through the IGA stage. Here we say final as it summarize all risk for the ESCO higher management decision.

## Slide 7: Project development steps
Evaluation team meeting for initial findings
Second team meeting to decide on project implementation
ESCO signs the project implementation agreement
Customer signs the agreement
ESCO Information Department
Survey using business plans, action plans, and screening tools
Meetings and inform customer
Payment database reporting
Potential from payment reports
Statistical potential tools
Credit rating assessment tools
ESCO Tools
Screening using tools and additional information
Customer data
Phone verification
Public information
Image Building
Senior management interviews, executive interviews
Creating sample frameworks and grid mapping
Identifying buy-in and its position
Meetings with decision-makers and operational heads
Customers understand the process and provide additional information
Questionnaire
Letter of Interesting
Customer Data
(Continuing)

## Slide 8: Project development steps
Third team meeting to finalize the proposal for IGA or framework agreement
ESCO signs the IGA implementation contract or framework contract
Customer signs
ESCO establishes potential savings and preliminary cost budgeting
Preliminary Survey and Report
Customer provides data during the survey
ESCO refines credit analysis and understands budget procedures
Further discussions on credit, financial matters, budget limits, and guarantees
Customer provides data
ESCO prepares the agreement and preliminary financial plan
Prepares the agreement for IGA or framework contract and preliminary financial plan
Customer evaluation
Agreement signing
Report template, analysis spreadsheet
Credit analysis tools
ESCO project financial tools
Agreement template
ESCO project financial tools.
(Continuing)

## Slide 9: Project development steps
Fourth team meeting to finalize the contract proposal
ESCO signs to implement the project
Customer signs
ESCO establishes EE potential and final project cost.
Conducts Investment Grade Audit (IGA)
Customer provides data and support for the audit
ESCO assesses technical, financial, and environmental risks, and conducts the final credit check
Risk analysis and final credit assessment
ESCO prepares the contract or annex and final financial plan
Finalizes the financial plan and contract for implementation (or annex to the framework contract)
Evaluation of customer
Negotiation continues until the contract or implementation annex is signed.
Report Template
Analysis Spreadsheet
Risk analysis tools
Customer Model
ESCO Project Financial Tools
Risk analysis and final credit assessment

## Slide 10: esco BIDDING
An enterprise owner can invite an ESCO to bid for an EE project
This usually occurs in the following context
The enterprise owner has been trained in the ESCO business model and can apply an appropriate selection system to select the project.
Usually government enterprises
A strong ESCO industry must exist
Steps
Pre-select a few ESCOs (usually 3-5)
Ask them to submit a detailed preliminary proposal
Present the proposed project and the guaranteed energy efficiency
Select one of the ESCOs to conduct a detailed audit and then implement

## Slide 11
Step by step development process
Objective: Prepare a new project for contract signing
Notes: We will not see in details all the steps presented in the previous slide, but just the more significant..
Trainees will be asked to share their experiences in developing ESCO business plans as part of an interactive session.

## Slide 12: SURVEY
Survey
  Identify potential enterprises with potential for EPC projects
  List of potential customers that
    - Marketing departments can approach them systematically after the screening process.
Survey was conducted from:
  List of potential customers taken from energy consumption database
    - Mainly in power companies implementing ESCO
  Photographing or simply observing buildings and industries as classified by ESCO development officers;
  Knowledge of the market and key organizations that may be the target audience;
  Enterprises networking through chambers of commerce or other associations;
  Advertising in newspapers, magazines or specialized publications;
  Industry/building management forums
Notes:   Prospecting is a process to identify potential customers in the market that could be interesting for an EPC project
  The objective of prospecting activity is to identify a list of potential customers that the marketing department can approach in a systematic way after a screening process

## Slide 13: SURVEY
Customer volunteer:
Customers that are not being met as a result of a systematic and planned approach
It could be organizations or companies that have met at trade fairs, customers that have heard about the ESCO concept and need more information.

## Slide 14: SURVEY
Target Customers:
A list of customers that have been collected by ESCO and are considered priority targets
Customers have been selected from an existing database, such as
Energy usage database
List of enterprises in the industry
Commercial Publications Department

## Slide 15: SURVEY
Target Customers:
Basic criteria for identifying factories.
Size of the factory
List of major factories by industry
Average price per unit of energy paid (the higher the unit price, the better)
Utilization factor (shows the number of using hours)
Fine has been paid

## Slide 16: SURVEY
The survey should be conducted according to:
  ESCO Business Plan: Constantly updated
  General goals, product types of ESCO
  Goals in the form of new products or new market development
EX 1: street lighting network
EX 2: ESCO wants to focus on industrial heat recovery systems

## Slide 17: SCREENING
What is screening?
The owner's selection method is through a systematic process
Eliminating factories without the potential to perform contracts effectively.
Or factories that have managers are not interested in the concept of contracts.
Screening Objectives:
Start thinking about the strategic value of doing a project for this plant
Decide before spending too much time and effort
Decide to prepare a official project and identify the elements to emphasize in the project.
Notes: Is the process where customers that have been identified through prospecting activity are qualified through a systematic process that allow to eliminate customers that do not represent interesting potential for a performance contract.

## Slide 18: SCREENING
Screening process
  Perform a quick analysis of the target base including:
Collect preliminary information of the plant
Assessing plant interest to ESCO
First level of reliability analysis

## Slide 19: SCREENING
Screening activities:
  A short interview or a 10 – 15 minutes phone call
    Discuss the major systems they have
    Recent renovations (often reducing EE potential)
    Issues they need to address in the short term (Identify the level of leadership to implement the project)
  Payment information (if any)
    Statistical analysis of plant energy usage
    Capacity factor or penalty for pick demand coefficient​
    Average cost per unit of energy
Notes: Next slide: Team meeting 1

## Slide 20: SCREENING
Screening activities:
  Creditworthiness analysis (level 1)
    Usually qualitative
    Reputation of the enterprise owner
    General economic context of the industry when the enterprise operates
    If public, preliminary analysis of annual report and balance sheet
  The level of detail depends on the type of contract:
    Sharing savings with finance; creditworthiness is a primary concern
    Ensuring savings: creditworthiness is primarily to protect against customer defaults during construction
Notes: Next slide: Team meeting 1

## Slide 21: Group meeting 1st
ESCO Development Manager and/or higher management meets with their development staff and technical staff
  Exchange information
  Discuss what is important for an EPC contract in the target plant
  Confirm implementation in the plant
Notes: Next slide: Team meeting 1

## Slide 22
Các bước khác nhau
Dự án được tài trợ như thế nào
Làm thế nào để đo mức tiết kiệm một cách minh bạch
Các điểm quyết định chính
Present to decision makers
  Present the ESCO concept and services and explain the project development process
  Learn more about your customer's strategy, operations, personnel, organization, and plant concerns
  Request for additional information: Survey questionnaire
Different steps
How is the project funded?
How to measure savings transparently
Key decision points
Notes: Next slide meeting 2
Questionnaire: Some ESCO request the customer to fill a questionnaire and assemble data. Other ESCO think this is too much at this stage and just slow down the momentum of the project development process and prefer to request information through meeting to discuss what is available then to confirm the list of requested information.

## Slide 23: Group SECOND meeting
  Confirm interest in continuing the development process with this client
  Confirm scope of preliminary audit
  Confirm level of involvement in preliminary audit:
    Preliminary
    Standards
    Details
Notes: Courtesy walk throug; client not interesting but a small report needed to conclude the relationship professionally
Standard: the usual level of detail.
Detailed: We really want this client and want to impress them.

## Slide 24: Group SECOND meeting
  Build a task list (to-do list) for the next phase;
  Allocate responsibilities for preparation:
    - Letter of interest ;
    - TOR for preliminary energy audit;
  Allocate resources to conduct preliminary energy audits;
  Building a budget;
  Audit Completion Timeline.

## Slide 25: LETTER OF INTEREST
Designed to reflect to customers including:
  Key steps to develop an energy efficiency project
  Goals and plant owner’s specific concerns
  Project development plan
  Requires cooperation with the client to collect electricity bills, visit the plant, and learn about energy operations and maintenance costs

## Slide 26: LETTER OF INTEREST
Advantage and disadvantage:
Advantage:
Confirm mutual understanding
Indicates that the plant owner understands and agrees to the process
Establish a foundation to build trust
Disadvantage:
Add additional signatures to the process
There may be a time delay.

## Slide 27: LETTER OF INTEREST
If the customer does not want to sign, it shows that:
  The contacted officer does not really have the authority to make a decision;
  Or the contacted officer does not want to work with you on a cooperative basis.
Both parties making and keeping their promises will eventually lead to a signed agreement.

## Slide 28: Preliminary audit
Objective/Scope:
  Survey plant equipment and operating systems
  Collect data on equipment performance, age, and condition
  Operating conditions/factors
  Listen to concerns of equipment operators and their operating experience
  Collect data to support preliminary engineering analysis for the project
  Identify a list of potential retrofits and the corresponding estimated range of potential energy efficiency
  Preliminary saving potential estimate <30%
  Preliminary cost estimate +30%

## Slide 29: Preliminary audit
Report:
  Discuss with the client the overall scope of the project
  Scope of energy efficiency
  Budget scope or payback period
  Demonstrate the ESCO’s ability to address the client’s key issues;
  Discuss the importance of the project to the ESCO.

## Slide 30: After preliminary audit
  Creditworthiness level II
    Ex: credit agency report
    Request factory owner to provide additional information
  Prepare an investment level audit agreement or framework agreement
    Some ESCOs prefer only an investment level audit agreement
    Others prefer not only a framework agreement that includes the investment level audit agreement but also the overall contract structure:
    Often takes longer to sign than a simple investment agreement
    Check client’s interest – make an appointment with their lawyer
    Specific project scope addendum is left blank. Will be added after investment audit and signing
Notes: Next slide meeting 3

## Slide 31: Group THIRD meeting
Objective:
  Review preliminary audit findings
  Review level 2 credit analysis
  Have a preliminary discussion of key project risk factors
  Review ESCO’s position with the client and share ratio
  Confirm ESCO’s interest in moving forward
  Finalise arrangements for investment level audit and framework agreements

## Slide 32: Group THIRD meeting
Objective (continue):
  Develop an action plan (list and to-do list) for the next phase of negotiating the agreement
  Allocate resources to present to the client and conduct further negotiations until the agreement is signed.
  Confirm the scope of the investment audit: the overall project including all applicable technologies or target programs as desired by the client
  Confirm the level of effort required for the investment audit
  Finalize the budget for the investment audit

## Slide 33: Presenting a preliminary energy audit
Objective:
  Provides a very brief overview of the results of the preliminary audit phase
    Savings Range
    Cost Range
  Represent client benefits in terms of customer strategic and tactical goals
    ESCOs shouldn't just sell energy efficency!
  Address client concerns and objections
  Build enthusiasm for the project and for the ESCO
  Present the framework agreement and investment level audit agreement
Notes: NEXT: IGA AGREMENT

## Slide 34: Investment level audit agreement or framework agreement
Investment level audit agreement objectives:
  Confirm terms of investment level audit
  Client exit and cost to be paid
  Proposal to bundle audit costs into project costs
  Framework agreement objectives
  Ensure client commitment and authorize ESCO to undertake entire project including investment level audit, design, implementation and measurement & verification
Notes: NEXT: DEVELOPMENT OF IGA

## Slide 35: implement investment level audit
Objective:
  Confirm the scope and cost reduction estimates presented in the preliminary audit report
  Develop strategies and EE solutions
    Sufficient preliminary design to build project cost
    Contingency cost
  Prepare a technical, financial report and performance parameters and implementing conditions
  Audit of investment level will be part of the contract
Notes: Next slide Risk Analysis IMPORTANT COMPONENT OF EPC

## Slide 36: Risk Analysis
  Risk Assessment
    In parallel with the implementation of investment level audit
  Review all aspects of the project to ensure that all critical elements are identified and addressed
  Risk analysis can identify
    Contract type,
    Level of obligation to the customer (safety factor applied to calculate savings)
    Contingency level (to avoid cost overruns)
    Conditions for project implementation
    Guarantee fee
Notes: Next Slide: Credit Worthiness

## Slide 37: CREDITWORTHY FOR DEBT Sustainability
  Final creditworthiness check before contract signing
  Level III creditworthiness analysis: For fully funded savings sharing contracts: use bank analysis to analyze the balance sheet and proposed projects
  For unfunded savings guarantee contracts: Perform further analysis to determine the commercial risk to the business owner (bankruptcy)
  Objective
  To provide the ESCO with the information needed to make decisions about the financial and commercial risks of the client.
Notes: Financial analysis next…..

## Slide 38: Financial Analysis
Objective:
Complete final financial analysis based on :
  Final scope of the project: With different options
  Consider financial risks
  The final project cost is based on completed quotes from all selected partners.
  Funding and investment program
    Finance charge for savings sharing contracts is fully funded
    Or third party offers finance
Notes: NEXT: TEAM MEETING 4

## Slide 39: Group 4th meeting
Objective of group meeting:
  Review investment level audit summary
  Review level III credit analysis
  Review internal risk analysis report
  Review financial plan and funding
  Review ESCO’s position with client and share ratio
  Confirm ESCO’s interest to continue developing the project with client

## Slide 40: Group 4th meeting
Objective of group meeting :
  Finalize arrangements for presentation of investment level audit report
  Prepare a contract
    - Or complete the annex of the framework agreement
  Confirm project scope
  Confirm necessary resources to implement project
  Develop a work list and contract negotiation plan
  Review contract terms
  Allocate resources to present to client and continue contract negotiation
Notes: NEXT: IGA PRESENTATION

## Slide 41: Investment level audit presentation
Objective of investment level audit presentation:
  Final presentation of all aspects of the project
  Provide project features, benefits and key elements of the project
  Present the completed energy service contract
  Address barriers/ remaining customer concerns

## Slide 42: Finalize the contract
  Select finally solutions after negotiation
  Update and adjust investment level audit
  Enterprise owner accepts and approves investment level audit
  Complete contract
  Negotiate contract
  Sign contract
Notes: NEXT: MEETING 5 FINAL CONCLUSION AND TIME TO CELEBRATE!!!!

## Slide 43: Group 5th meeting
Objective:
  Share information obtained during the negotiation phase with the technical department
  Review key elements of the contract that the technical department should know
  Define an action plan, allocate resources, and open accounts in accounting software.

## Slide 44
Thank you!