## Slide 1
MODULE 12:
RISKS AND RISK MITIGATION FOR ESCO PROJECTS
By PhD: Nguyen Xuan Quang

## Slide 2
OBJECTIVE OF MODULE
Identify and control risks for an ESCO

## Slide 3: RISK ANALYSIS
Objective: Assess and solve ESCO risks
ESCO projects often face many risks due to financial, technical, operational investments and long-term management.
Identifying and managing risks from the early stages will help the project avoid potential problems and ensure success.

## Slide 4: Risk Classification in ESCO Project
Financial risks: Relate to capital mobilization, investment costs, and the ability to recover capital from energy efficiency.
Technical risks: Regarding equipment performance, technology, and the ability to achieve committed energy efficiency.
Operation and maintenance risks: Relate to the operation and maintenance of the system during the contract period.
Legal risks: Issues relate to compliance with laws, regulations, and contracts.
Market risk: Changes in energy prices or economic and policy fluctuations.

## Slide 5
RISK IDENTIFICATION AND MINIMISATION STRATEGY
ESCO must become a risk assessment expert.
  Risk management ensures that results are in full compliance with expectations.
  Requires a rigorous internal process
  Normally, a risk manager is appointed within the ESCO and internal audits (or verifications) of project risks are performed
  Independent of the project team

## Slide 6
RISK IDENTIFICATION AND MINIMISATION STRATEGY
  Client Selection
  Audit
  Design
  Construction Cost Assessment
  Execution Management
  Health and Safety
  Measurement and Verification of Solutions
Sources of project risk :
  Paying for energy efficiency
  Customer financial strength
  Financial parameters
  Changing building use
  Evaluating savings
  Maintaining long-term energy efficiency
  Customer behavior

## Slide 7
RISK CONTROL – CUSTOMER SELECTION
Source
Customers do not have any motivation.
Solution
Exercise

## Slide 8
RISK CONTROL – CUSTOMER SELECTION
Source
Customers do not have any motivation.
Solution
Use a staged marketing approach to see how the client is doing.
Avoid working with a project that have obvious conflict of interest.

## Slide 9
RISK CONTROL – AUDIT
Source of error
  The client provided incomplete or incorrect data.
  Inappropriate assumptions were made in the audit.
  Not to calculate a margin of safety.
  Incorrect selection of base year.
Solution
Exercise

## Slide 10
RISK CONTROL – AUDIT
Source of error
  The client provided incomplete or incorrect data.
  Inappropriate assumptions were made in the audit.
  Not to calculate a margin of safety.
  Incorrect selection of base year.
Solution
  Adjust terms in case of incorrect or incomplete information in the contract.
  Document all assumptions in writing and ask the customer to confirm them.
  Introduce adequate contingency measures.
  Measure all key parameters.

## Slide 11
RISK CONTROL – DESIGN
Source of error
Existing plans and specifications are not up to date.
Use new equipment and procedures.
Solution
Exercise

## Slide 12
RISK CONTROL – DESIGN
Source of error
Existing plans and specifications are not up to date.
Use new equipment and procedures.
Solution
  Verify data in plans and specifications. Measure.
  Avoid demonstrations of new equipment.
  Work carefully with less familiar processes
  Include a return clause for defective equipment in the contract.

## Slide 13
RISK CONTROL – CONSTRUCTION COST ASSESSMENT
Source
  The estimate understates fixed costs.
  The estimate too many overhead costs
  The estimate understates site costs or omitting them completely.
Solution
Exercise

## Slide 14
RISK CONTROL – CONSTRUCTION COST ASSESSMENT
Source
  The estimate understates fixed costs.
  The estimate too many overhead costs
  The estimate understates site costs or omitting them completely.
Solution
  Obtain quotes from contractors regarding fixed costs before submitting a proposal to the client.
  Introduce some contingency measures.
  Include a clause in the contract allowing for cost adjustments up or down within the range of 10 – 15% of the estimated cost.
  Safety, cleanliness, scaffolding, fencing, sanitation and on-site services.

## Slide 15
RISK CONTROL – CONSTRUCTION PHASE
Source
The longer the field work, the higher the interim funding amount and the shorter the payback period, if the contract is for a fixed term.
Solution
Exercise

## Slide 16
RISK CONTROL – CONSTRUCTION PHASE
Source
The longer the field work, the higher the interim funding amount and the shorter the payback period, if the contract is for a fixed term.
Solution
  For fixed term contracts, the ESCO can specify a start date for the payback period.
  Include a provision in the contract that allows the ESCO to use the savings payment portion of the first few months to pay interest.

## Slide 17
RISK CONTROL – ENVIRONMENT AND HEALTH
Source
  PCBs or Asbestos Removal
  Work is performed in a building that has air quality and comfort issues. ESCOs can address these issues, at the cost of lower energy savings.
Solution
Exercise

## Slide 18
RISK CONTROL – ENVIRONMENT AND HEALTH
Source
  PCBs or Asbestos Removal
  Work is performed in a building that has air quality and comfort issues. ESCOs can address these issues, at the cost of lower energy savings.
Solution
  Find out about current regulations
  Gather all the information about the current condition of the building before implementing solutions.

## Slide 19
RISK CONTROL – MEASURE AND VERIFY SOLUTIONS
Source
The impact of solutions is difficult to predict. Depends on:
  Behavioral Changes
  Equipment Performance
  Equipment Malfunctions
Solution
Exercise

## Slide 20
RISK CONTROL – MEASURE AND VERIFY SOLUTIONS
Source
The impact of solutions is difficult to predict. Depends on:
  Behavioral Changes
  Equipment Performance
  Equipment Malfunctions
Solution
  Excludes behavioral solutions
  Includes safety factor when calculating savings
  Manufacturer/contractor guarantees performance and operation warranty.
  Uses proven technology and equipment

## Slide 21
RISK CONTROL – PAYING FOR EE
Source
The energy efficiency project did not achieve the predicted level of efficiency.
Solution
Exercise

## Slide 22
RISK CONTROL - PAYING FOR EE
Source
The energy efficiency project did not achieve the predicted level of efficiency.
Solution
Audit and add terms to the contract:
  Better control over audits and assumptions.
  Guarantee a lower savings level than the calculated savings.
  Internal security fund (established by ESCO)
  External savings insurance (very rare)

## Slide 23
RISK CONTROL – CUSTOMER FINANCIAL STRENGTH
Source
The client lacks the level of financial stability required for a long-term contract.
Solution
Exercise

## Slide 24
RISK CONTROL – CUSTOMER FINANCIAL STRENGTH
Source
The client lacks the level of financial stability required for a long-term contract.
Solution
  Apply credit assessment methods used by banks
  Apply higher interest rates or profit margins to projects of customers with poor financial status.
  Transfer responsibility to banks.

## Slide 25
RISK CONTROL – FINANCIAL PARAMETERS
Source
The fluctuation of:
  Energy Prices
  Interest Rates
  Inflation
All of these fluctuations can significantly reduce your savings potential
Solution
Exercise

## Slide 26
RISK CONTROL – FINANCIAL PARAMETERS
Source
The fluctuation of:
  Energy Prices
  Interest Rates
  Inflation
All of these fluctuations can significantly reduce your savings potential
Solution
  Contract Terms: Set a floor price for energy to avoid large reductions in savings.
  Analyze the sensitivity of the payback period to changes in interest rates and inflation rates.
  It is possible to choose the contract duration according to the most pessimistic scenario.

## Slide 27
RISK CONTROL – CHANGES IN BUILDING USE
Source
The purpose of the building or industrial enterprise changes significantly. Therefore, the predicted savings cannot be achieved.
Solution
Exercise

## Slide 28
RISK CONTROL – CHANGES IN BUILDING USE
Source
The purpose of the building or industrial enterprise changes significantly. Therefore, the predicted savings cannot be achieved.
Solution
Include a clause in the contract that allows for adjustments to savings in case of changes to initial data.

## Slide 29
RISK CONTROL – SAVINGS ASSESSMENT
Source
  Complex Savings Calculation Method
  ESCO changes the base year in case of change in building use or other changes.
Solution
Exercise

## Slide 30
RISK CONTROL – SAVINGS ASSESSMENT
Source
  Complex Savings Calculation Method
  ESCO changes the base year in case of change in building use or other changes.
Solution
  Use a simple savings calculation method.
  Provide detailed examples of invoicing during the negotiation phase and develop the method with the client.
  Use a fixed payment to quickly prepare invoices for savings.
  Include an arbitration clause in the contract that can mediate between the parties in case of dispute.

## Slide 31
RISK CONTROL – MAINTAINING LONG-TERM SAVINGS
Source
  Restructuring
  Work interruptions
  Changes in use or operating procedures
  Inadequate maintenance
  Sudden increase in maintenance costs
  Changes in regulations
Solution
Exercise

## Slide 32
RISK CONTROL – MAINTAINING LONG-TERM SAVINGS
Source
  Restructuring
  Work interruptions
  Changes in use or operating procedures
  Inadequate maintenance
  Sudden increase in maintenance costs
  Changes in regulations
Solution
  Use qualified staff and establish a maintenance plan.
  Establish realistic maintenance and contingency budgets.
  Train staff.
  Avoid assumptions about maintenance and repair responsibilities.
  Establish long-term maintenance costs.

## Slide 33
RISK CONTROL – CUSTOMER BEHAVIOR
Source
  New Management
  The enterprise has just moved.
  The client has decided to terminate the contract.
Solution
Exercise

## Slide 34
RISK CONTROL – CUSTOMER BEHAVIOR
Source
  New Management
  The enterprise has just moved.
  The client has decided to terminate the contract.
Solution
  Implement energy efficiency contracts and related complex documentation.
  Establish a buyback price to protect profit margins.
  Niche market execution: the most stable market.

## Slide 35
Thank you !