## Slide 1
Module 6:
EPC CONTRACT DEVELOPMENT PROCESS
By PhD. Nguyen Thi Mai Anh

## Slide 2: Discuss question
DO YOU KNOW THE MAIN STEPS
IN CONDUCTING AN EPC CONTRACT?????

## Slide 3: MAIN STEPS IN DEVELOPING AN EPC CONTRACT
CLIENT QUALIFICATION
PRELIMINARY
AUDIT
INVESTMENT
GRADE AUDIT (IGA)
FINANCING
M&V - PAYMENT
O&M
CONSTRUCTION COMMISSIONGS
ENGINEERING & DESIGN

## Slide 4: 1. CLIENT QUALIFICATION
Financial Assessment
Is the client creditworthy for customer financing (Guaranteed Savings model)?
Can the client secure financing independently, or will they rely on third-party lenders?
If ESCO financing is required (Shared Savings model), does the project meet lender requirements?
Commitment to Energy Efficiency
Is the client genuinely committed to implementing energy efficiency projects?
Do they have a long-term vision for sustainability and cost savings?
Are they willing to engage in performance-based contracts?

## Slide 5: 2. PRELIMINARY AUDIT
Used to quickly determine if a cost effective process can be developed
Followed by an audit report with cost and savings estimates and a proposal toperform an investment grade audit if warranted
Typically done at no cost to customer

## Slide 6: 3. INVESTMENT GRADE AUDIT (IGA)
If the IGS confirms the finding of the preliminary audit:
No cost to the customer if the findings of preliminary audit are not confirmed
Financial plan and MV plan are prepared at this stage

## Slide 7: 4. FINANCING
Development of financing plan
ESCO helps arrange financing
Approval by lender

## Slide 8: 5. ENGINEERING & DESIGN
ESCO acts as project manager
Ensure that specifications and drawings are prepared

## Slide 9: 6. CONSTRUCTION COMMISSIONGS
Phase | Customer Responsibilities | ESCO Responsibilities
Equipment Procurement | Provide necessary approvals and site access | Select, procure, and ensure the quality of equipment
Installation & Construction | Coordinate with ESCO and contractors for site readiness | Invite bids (if necessary) from qualified contractors and supervise installation
Construction Supervision | Provide feedback and ensure compliance with site regulations | Manage contractors, oversee installation, and ensure adherence to project scope
Start-up & Commissioning | Support the process and provide operational staff if needed | Conduct testing procedures, ensure proper start-up, and verify performance
Final Inspection & Handover | Sign off on completion and confirm satisfaction | Ensure installation meets contractual and operational standards
Ensure Savings Are Delivered | Monitor ongoing savings and provide operational feedback | Implement performance monitoring, verify guaranteed savings, and provide post-installation support

## Slide 10: 7. O&M
Equipment must operated and mainained according to specifications to ensure that energy savings will materialize
Maiternance is ESCO’s responsibility if in shared savings
Mainternance need to be negotiated if in guaranteed

## Slide 11: 7. O&M
Equipment must be operated and maintained according to specifications to ensure that energy savings are realized.
Maintenance Responsibilities:
    Under Shared Savings: ESCO is responsible for maintenance.
    Under Guaranteed Savings: Maintenance responsibility must be negotiated between the Client and ESCO to ensure proper upkeep and sustained energy performance.
    Training of Operating Personnel:
      ESCO should provide training to the Client’s personnel on proper equipment operation and maintenance best practices.
      Clear protocols and guidelines should be established to ensure long-term efficiency and savings.

## Slide 12: 8. M&V - PAYMENT
M&V
Could be short-term or long-term
Saving demonstration according to the MV plan
MV reports produced annlually
PAYMENT
Invoicing of saving to customer, if shared savings agreement
Emission of check for shortfall of saving if guaranteed savings agreement

## Slide 13: KEYP COMPONENTS OF EPC
M&V
Could be short-term or long-term
Saving demonstration according to the MV plan
MV reports produced annlually
PAYMENT
Invoicing of saving to customer, if shared savings agreement
Emission of check for shortfall of saving if guaranteed savings agreement

## Slide 14
Thank you!