## Slide 1
PhD. Nguyen Thi Mai Anh
Module 7:
EPC Contracts: Key Contents
& Risk of an EPC contract

## Slide 2: KEY CONTENTS
Definition of the baseline conditions,
Details of the EE measures to be implemented,
Responsibilities of ESCO and customer during project development and implementation.
Services to be provided by ESCO
Equipment selection and installation
Construction and installation schedule
ESCO and customer obligations during construction
8. Equipment ownership
9. ESCO performance guarantees
10. ESCO compensation
11. Specification of baseline conditions
12. Savings calculation approach and formulas
13. M&V plan
14. Dispute resolution procedures

## Slide 3: KEY CONTENTS
Customer | is the owner of facility where energy efficiency measures will be implemented and will be the final user of the project implemented.
ESCO | is the professional Project Leader and is responsible for technical and financial aspect of Project implementation.
Energy Savings | the savings in electricity costs resulting from reduced energy consumption and demand in the Facility over a period of time agreed upon by the Parties hereto
Baseline | is a representation of the energy usage of the facility included in the project considering that equipment and operating context are in line with a normal operation and good working condition.
Energy Efficiency measures | means the upgrade, modification or replacement of mechanical, electrical equipment and control that were analyzed in the investment grade audit and that have been approved by the CUSTOMER for implementation in the project.
Project cost | Total cost of the Project to CUSTOMER includes: investment cost, finance cost, labour cost,administrative cost..

## Slide 4: KEY CONTENTS
LITS OF PROVIDED SERVICES
Project development and design
Project financing
Project implementation
Energy management services
Etc.

## Slide 5: KEY CONTENTS
WORK DESCRIPTION
Summary of the modification of the system that consume energy within the facility, according to the proposals contained in the IGS
Summary of any additional work required by the customer
BASIC PRINICIPLES
Project financing implementation by ESCO
Project payment from the achieved saving
Shared planning and preparation
Mutual collaboration

## Slide 6: KEY CONTENTS
PROJECT PHASES
Preparatory activities for the implementation of energy efficiency measures
Implementation of energy efficiency measures
Operation, maintenance and invoicing of energy savings until project reimbursement
OTHER ELEMENTS
Responsibilities (ESCO, customer)
Commencement/ Completion date
Specifications
Procurement and work
Project acceptance, work warranties
Project financing, financial plan, payment
Final estimation of project costs
Saving M&V, M&V reporting
Force majeure, recolution of disputes
Etc.

## Slide 7: Risks for an EPC Contract
Financial risk
Audit and design risk
Construction risk
Performance risk
Customer-related risk

## Slide 8: Financial Risks
RISKS:
Energy price fluctuations
Exchange rate fluctuations
Interest rates
RISK MITIGATION:
Set a baseline energy price for calculations
Perform sensitivity analysis on the project’s payback period with respect to interest rates and inflation, and select an appropriate contract term
Insurance against foreign exchange risk.

## Slide 9: Audit Risks
RISKS
Client provides incomplete or inaccurate data
Inaccurate assumptions
Insufficient contingency in calculations
RISK MITIGATION
Include adjustment clauses in case incomplete or inaccurate data is discovered
Document all assumptions and require client verification
Apply adequate contingency allowances.
Develop a good baseline and get the client to agree to it

## Slide 10
DESIGN RISK
RISKS
Drawings and technical specifications are not updated.
Use of unproven technology.
RISK MITIGATION
Verify the data of drawings and technical specifications.
Avoid using unproven equipment.
Work carefully, especially with unfamiliar processes.
Always check a reference sample for a product.
Avoid special designs available from only one supplier.

## Slide 11: CONSTRUCTION COST RISKS
RISKS
Some ESCOs are unfamiliar with managing turnkey projects.
Lack of experience in cost estimation.
RISK MITIGATION
Obtain contractor bid records before making proposals to clients.
Maintain contingencies: Do not underestimate transportation costs, client costs, site costs, insurance, contracts, and safety requirements.

## Slide 12: CONSTRUCTION DELAY RISKS
CONSTRUCTION DELAY RISKS
RISKS
Construction delays increase financial costs and shorten payback periods if the contract has a fixed term.
RISK MITIGATION
For fixed-term contracts, set the start date as the date when all solutions are in place.
Include a clause in the contract that allows the ESCO to start recovery as soon as the first savings are achieved.
Clearly define the savings calculation method to ensure transparency and avoid disputes related to project delay

## Slide 13: SAVINGS RISKS
RISKS
Complexity of savings calculation methods.
Changes in building or operational parameters.
RISK MITIGATION
Use a simple avoided cost method.
Include a baseline adjustment clause in the contract.
Involve the client in developing the M&V savings method.
Resolve disputes through arbitration.

## Slide 14
ACTUAL SAVINGS RISKS
RISKS
Equipment efficiency.
Equipment failure.
Customer behavior.
RISK MITIGATION
Plan to implement simple solutions first to achieve early savings.
Include a safety factor in energy savings calculations in the contract.
Have manufacturers/contractors guarantee performance and operation.
Use proven equipment and technology.
Include a baseline adjustment clause in the contract.

## Slide 15
CUSTOMER BEHAVIOR RISKS
RISKS
Operational changes.
Changes in usage hours and operating hours.
Inadequate maintenance.
Increased maintenance costs.
RISK MITIGATION
Include a baseline scenario clause in the contract.
Agree on a maintenance plan.
Train the client’s team.
Avoid assumptions related to maintenance and asset disposal.
Stabilize long-term maintenance costs.

## Slide 16
CUSTOMER BEHAVIOR RISKS
RISKS
New client management.
Client decides to terminate the contract.
Poor business performance..
RISK MITIGATION
Make sure that customer clearly understand and agree to the terms
Include termination costs for the client in the contract.
Conduct a thorough client analysis.

## Slide 17: Discuss question
PROBLEMS WHAT YOU OFTEN ENCOUNTER – THE SOLUTION?
Group discussions and presentations

## Slide 18
Thank you!